## Sheet1
NMR Spectrometer Training Manual: Schedule
Client and SME: CHEM-3206: Advanced Organic Chemistry Lab Instructor
| Documentation Project Manager: Rachelle Gervacio |  | About (click here) |  |  | October (2019) | [30 empty] | November (2019) | [29 empty] | December (2019)
| Project Start Date: October 2, 2019 Deadline: December 2, 2019 |  | Legend (click here) |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24 | 1900-01-25 | 1900-01-26 | 1900-01-27 | 1900-01-28 | 1900-01-29 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24 | 1900-01-25 | 1900-01-26 | 1900-01-27 | 1900-01-28 | 1900-01-29 | 1900-01-30
| Task(s) | Resource(s) | Start | End | No. Days | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T
Task Description | 1) Plan |  | 2019-10-02 | 2019-10-09 | 6
Plan (Aug. 1/18 – Aug. 13/18) | Discuss the project requirements with the client. | Project Manager | 2019-10-02 | 2019-10-02 | 1 | bar: October (2019) 2
Determine the project’s scope and goals. | Define the project’s scope and goals. | Project Manager | 2019-10-03 | 2019-10-03 | 1 | bar: October (2019) 3
Estimate the project’s schedule, budget, and resources. | Estimate the project’s schedule, budget, and resources. | Project Manager | 2019-10-04 | 2019-10-04 | 1 | bar: October (2019) 4 to October (2019) 6
| Create a document outline and content plan. | Project Manager | 2019-10-07 | 2019-10-09 | 3 | bar: October (2019) 7 to October (2019) 9
Discuss plan with team members and stakeholders.
| 2) Design |  | 2019-10-10 | 2019-10-15 | 4
Design (Aug. 14/18 – Sept. 8/18) | Define usability and accessibility goals. | Project Manager | 2019-10-10 | 2019-10-10 | 1 | bar: October (2019) 10
Conduct audience and task analysis. | Conduct audience and task analysis. | Project Manager | 2019-10-11 | 2018-10-12 | 2 | bar: October (2019) 11 to October (2019) 14
Identify information design, usability, and accessibility goals. | Identify appropriate writing style and style guide. | Project Manager | 2019-10-15 | 2018-10-15 | 1 | bar: October (2019) 15
| 3) Develop |  | 2019-10-10 | 2019-11-28 | 33
| Writing |  | 2019-10-10 | 2019-11-13 | 22
| Research project topic and gather sources. | Project Manager | 2019-10-10 | 2018-10-15 | 3 | bar: October (2019) 10 to October (2019) 15
| Review and modify content from existing documentation. | Project Manager | 2019-10-16 | 2019-10-16 | 1 | bar: October (2019) 16
| Write a draft for conceptual, procedural, and reference topics. | Project Manager | 2019-10-17 | 2019-11-13 | 18 | [43 empty] | M | bar: October (2019) 17 to October (2019) 31
| Discuss training manual concepts, procedures, and references with the project manager. | Subject-Matter Expert | 2019-10-15 | 2019-10-15 | 1
| Editing |  | 2019-11-19 | 2019-11-21 | 4
| Revise draft for its accordance with its rhetorical situation and SME feedback. | Project Manager | 2019-11-19 | 2019-11-19 | 1
| Revise draft for organization, consistency, and content gaps and accuracy. | Project Manager | 2019-11-20 | 2019-11-21 | 2
| Revise draft for its accordance with the specified style guide. | Project Manager | 2019-11-22 | 2019-11-22 | 1
| Proofreading |  | 2019-11-25 | 2019-11-28 | 3
| Review, revise, and finalize the draft for mechanical and formatting errors. | Project Manager | 2019-11-25 | 2019-11-28 | 3 | [58 empty] | M
| Illustrating |  | 2019-11-14 | 2019-11-18 | 3
| Create and edit photos, screenshots, and icons. | Project Manager | 2019-11-14 | 2019-11-18 | 3
| Testing |  | 2019-11-26 | 2019-11-26 | 1
| Test and revise documentation for errors and inconsistencies | Project Manager | 2019-11-26 | 2019-11-26 | 1
| Test documentation with the project manager | Subject-Matter Expert | 2019-11-26 | 2019-11-26 | 1
| 4) Produce |  | 2019-11-29 | 2019-12-03 | 3
| Identify production requirements and format. | Project Manager | 2019-11-29 | 2019-11-29 | 1
| Review and approve the finished document. | Subject-Matter Expert | 2019-12-02 | 2019-12-02 | 1
| Gain approval from the client to finalize and publish the document. | Project Manager | 2019-12-02 | 2019-12-02 | 1
| Distribute the finalized document to the client. | Project Manager | 2019-12-03 | 2019-12-03 | 1 | [63 empty] | M
| 5) Evaluate |  | 2019-12-10 | 2019-12-13 | 4
| Evaluate the project’s final budget and schedule development. | Project Manager | 2018-12-10 | 2018-12-11 | 2
| Meet with the client to discuss the final document, areas for improvement, and overall project effectiveness. | Project Manager | 2018-12-12 | 2018-12-12 | 1
| Create a report that summarizes documentation results. | Project Manager | 2018-12-13 | 2018-12-13 | 1 | [73 empty] | M
|  | Total days | 50 days